# TravelWise - Product Backlog Document

Project Duration: 8 Months  
Planning Phase: Initial 4 Months  
Development Phase: Final 4 Months (Approx. 16 Weeks)  
Sprint Duration: 4 Sprints, ~3 Weeks Each (Hybrid Agile)

- Project Overview

Project Name: TravelWise  
Objective: Centralized travel web application offering itinerary management, AI-driven recommendations, expense tracking, local guide booking, and seamless user experience.

- Key Features and Requirements Summary

# Key Features:
- Travel Itinerary Management
- Expense Monitoring
- Local Guide Booking
- AI Recommendations (hotels, restaurants, safety, etc.)
- Review and Rating Aggregation
- Responsive, Accessible UI
- Public API Integrations (e.g., flights, weather, maps)

# Preliminary Technical Requirements:
- Secure user authentication and data encryption
- Integration with booking and recommendation APIs
- AI-powered recommendation engine
- Web-based responsive UI/UX
- Database design and CI/CD pipeline

- Full 8-Month Product Backlog Plan

# Phase 1: Planning & Design (Months 1–4)
Milestones:
- Requirements Gathering
- Competitor Analysis
- Market Research
- High-Level Use Case Diagrams
- Data Flow Diagrams (DFDs)
- Entity Relationship Diagrams (ERDs)
- User Interface Wireframes (Figma)
- Prototype Demonstrations
- SRS Document Creation

Outputs:
- Validated business requirements
- Approved system design (mockups, flows)
- Technical feasibility assessment
- Stakeholder feedback incorporated into designs

# Phase 2: Development Sprints (Months 5–8)

4. Epics Overview
Below is a list of all primary epics to support the TravelWise product.

- User Authentication & Account Management

- User Profile Management

- User Dashboard & Trip Overview

- Hotel Booking Management

- Flight Booking Management

- Transportation Booking

- External API Integration

- Booking Confirmation & Review

- Responsive Design & Accessibility

- Analytics & Metrics Tracking

- AI-Powered Travel Suggestions

5. Sprint Plan with Epics and User Stories
Each sprint below outlines its goal, associated epics, and detailed user stories to deliver incremental value while adhering to the MVP scope.

Sprint 1: Authentication, Profile & Dashboard Setup
Goal: Enable users to register, log in, manage their profile, and view their dashboard.
Epics Covered:
-  User Authentication & Account Management

- User Profile Management

- User Dashboard & Trip Overview

User Stories:
- As a user, I want to register using email/password, so that I can create an account.

- As a user, I want to securely log in and log out, so that my personal data is protected.

-  As a user, I want to edit my profile (name, contact info), so that I can keep my info up to date.

-  As a user, I want to view my travel dashboard, so that I can manage trips and access tools in one place.

-  As a developer, I want password hashing and JWT token authentication implemented, so that login is secure.

-  As a developer, I want to validate input fields for login/register/profile, so that invalid data is prevented.

Sprint 2: Hotel, Flight & Transport Management
Goal: Allow users to search and manage bookings for hotels, flights, and transportation.
Epics Covered:
-  Hotel Booking Management

-  Flight Booking Management

-  Transportation Booking

-  External API Integration (Phase 1)

User Stories:
-  As a user, I want to search and book hotels at my destination, so that I can arrange accommodation.

-  As a user, I want to search and book flights based on my travel dates, so that I can plan efficiently.

-  As a user, I want to manage my flight and hotel bookings from one place, so that I don’t lose track.

-  As a user, I want to search and book local transport (e.g. taxi/shuttle), so that I can move around easily.

-  As a developer, I want to integrate hotel and flight APIs (Skyscanner, RapidAPI), so that users get live booking options.

Sprint 3: Booking Summary & Itinerary Management
Goal: Finalize user booking flow, enable creation of personalized itineraries, and ensure booking and itinerary data is saved, accessible, and trackable, including messaging capabilities for local guide coordination.

Epics Covered:
-  Booking Confirmation & Review

-  External API Integration (Phase 2)

- Itinerary Management

- User to guide messaging system

User Stories:
-  As a user, I want to receive a booking confirmation summary, so that I can verify all travel details.

-  As a user, I want to cancel or modify my bookings if needed, so that I can adjust plans as required.

-  As a user, I want to create and organize my itinerary with booked locations, so that I can plan my trip day by day.

-  As a user, I want to rearrange or remove itinerary items using a drag-and-drop interface, so that I can easily update my plans.

-  As a user, I want the itinerary to display travel time estimates and daily views, so that I can efficiently schedule activities.

-  As a user, I want to be able to send a message to a guide from the messaging center.

-  As a user, I want to see all past conversations in the messaging center.

-  As a developer, I want itinerary updates to autosave with proper input validation, so that users don't lose data and errors are prevented.

Sprint 4: AI Suggestions, Functional Testing, Accessibility & Polish
Goal: Deliver AI-based travel suggestions and polish the user experience for release.
Epics Covered:
- AI-Powered Travel Suggestions

- Responsive Design & Accessibility

- Analytics & Metrics Tracking

- Functional Testing and Quality Assurance

- Booking Confirmation & Review (continued)

User Stories:
-  As a user, I want to get AI recommendations for destinations, hotels, and restaurants, so I can explore new options.

-  As a user, I want the platform to work on mobile and desktop seamlessly, so that I can access it anywhere.

-  As a visually impaired user, I want screen reader and keyboard support, so that I can use the app independently.

-  As a developer, I want to add disclaimers near AI suggestions, so that users understand limitations.

-  As a product owner, I want final release checks for performance and accessibility to be done, so that launch is smooth.

-  As a developer, I want to set up basic analytics on booking flow, so that we can improve conversion rates.

-  As a developer, I want to test that itinerary builder correctly saves and loads user data.

-  As a developer, I want to test form validation (Login, Sign up, and guide messaging).

-  As a developer, I want to verify booking flow works correctly so that users can successfully complete their reservations.

-  As a product owner, I want to track user activity (like completed bookings), so that I can evaluate engagement.

6. Risk Management by Sprint

Each sprint includes specific risks (e.g., auth flaws, AI hallucination) and mitigation (e.g., input validation, fallback APIs, disclaimers).

7. MVP Definition

MVP Includes:
- Secure registration & login
- Trip and itinerary builder
- Expense tracking
- AI suggestions
- Guide booking
- Review aggregation
- Mobile-friendly, accessible UI
- Analytics and KPIs